## Index
Bug Report For YallaKora APP
Reporter | Omar Abo Smrh
Title | Software Test Engineer
version | Android v1.0
Report To | Instabug Company
Date | 2022-07-08
Reviewed By

## Bug Report_v1.0
ID | Module | TITLE | PRECONDITION | Test Data | STEPS | Actual Result | Expected Result | Severity | Priority | Attachement | Environment | Network | Assigned To | Status
YallaKora_001 | Matchs Module'مباريات' | No exit button for calender | The user can Download yallakora app from app store or google play and the app should be accessable. | no test data nedded | 1-open yallakora app. 2-navigate to 'مباريات'. 3- click on 'calender'. | can't exit calender and there is no exit button for calender | preview exit button in calender | Major | Hight | https://drive.google.com/file/d/1FCJAlKQSyzjQZQERtwUJmnCn_CabtKF3/view?usp=sharing | Samsung Galaxy A6+ One Ui version 2.0 Android Version 10 | Wifi/Data | Developer X | To Do
YallaKora_002 | Leagues'بطولات' | statstics image broken in qatar league | The user can Download yallakora app from app store or google play and the app should be accessable. | no test data nedded | 1-open yallakora app. 2-navigate to 'بطولات'. 3- click on 'دوري نجوم قطر'. 4- click on 'احصائيات' | all images are broken | images should be preview | Moderate | Medium | https://drive.google.com/file/d/1eqY-7us1ZjZ31Fn9ofeEX9j9yhkwgWYt/view?usp=sharing | Samsung Galaxy A6+ One Ui version 2.0 Android Version 10 | Wifi/Data | Developer X | To Do
YallaKora_003 | Home 'الرئيسية' | invalid date news in home page | The user can Download yallakora app from app store or google play and the app should be accessable. | no test data nedded | 1-open yallakora app. 2-check news date | invalid date news | date should be preview | Minor | Medium | https://drive.google.com/file/d/1tCCSgVUC7yi4g4M8bJFUNmacfIHdgEaz/view?usp=sharing | Samsung Galaxy A6+ One Ui version 2.0 Android Version 10 | Wifi/Data | Developer X | To Do
YallaKora_004 | Matchs Module'مباريات' | news not clickable in matchs at 'دوري نجوم قطر' | The user can Download yallakora app from app store or google play and the app should be accessable. | no test data nedded | 1-open yallakora app. 2-navigate to 'مباريات'. 3- click on 'دوري نجوم قطر'. 4- click on any one of news 'اخبار' | news not clickable in matchs | news should be clickable and should be preview | Moderate | Medium | https://drive.google.com/file/d/1kdbd6zMlv-abxC3S_zzTHkjVCr9ARDRu/view?usp=sharing | Samsung Galaxy A6+ One Ui version 2.0 Android Version 10 | Wifi/Data | Developer X | To Do
YallaKora_005 | Leagues'بطولات' | "قائمة الهدافين" image broken in qatar league | The user can Download yallakora app from app store or google play and the app should be accessable. | no test data nedded | 1-open yallakora app. 2-navigate to 'بطولات'. 3- click on 'دوري نجوم قطر'. 4- click on 'قائمة الهدافين' | all images are broken | images should be preview | Minor | Low | https://drive.google.com/file/d/1NdMJwouOd3BR1BUmAUJnAUX1w0rxqWV_/view?usp=sharing | Samsung Galaxy A6+ One Ui version 2.0 Android Version 10 | Wifi/Data | Developer X | To Do
YallaKora_006 | Leagues'بطولات' | "قائمة صانعي الأهداف image broken in qatar league | The user can Download yallakora app from app store or google play and the app should be accessable. | no test data nedded | 1-open yallakora app. 2-navigate to 'بطولات'. 3- click on 'دوري نجوم قطر'. 4- click on 'قائمةصانعي الاهداف' | all images are broken | images should be preview | Minor | Low | https://drive.google.com/file/d/1zrzlrttNa-KcKSNDOfeaoljqAVJF7ovG/view?usp=sharing | Samsung Galaxy A6+ One Ui version 2.0 Android Version 10 | Wifi/Data | Developer X | To Do
YallaKora_007 | Favoirite Teams 'فرقك' | ui issue in favorite teams | The user can Download yallakora app from app store or google play and the app should be accessable. | no test data nedded | 1-open yallakora app. 2-navigate to 'فرقك'. 3- add favorite team ans check ui | ui not responsive | ui should be suitable with size screen | Minor | Medium | https://drive.google.com/file/d/1z8mvDxrMGhlL0yp5K0XHDGsqckfvbaPU/view?usp=sharing | Samsung Galaxy A6+ One Ui version 2.0 Android Version 10 | Wifi/Data | Developer X | To Do
YallaKora_008 | Matchs Module'مباريات' | "قائمة الهدافين" image broken in leagues | The user can Download yallakora app from app store or google play and the app should be accessable. | no test data nedded | 1-open yallakora app. 2-navigate to 'مباريات'. 3- click on 'دوري نجوم قطر'. 4- click on 'قائمة الهدافين' | all images are broken | images should be preview | Minor | Medium | https://drive.google.com/file/d/1QGmDtz9RfykNRYZcV-untQaXCz8rSpFK/view?usp=sharing | Samsung Galaxy A6+ One Ui version 2.0 Android Version 10 | Wifi/Data | Developer X | To Do
YallaKora_009 | Leagues'بطولات' | no preview for full name of teams table rank and league ui issue and there is no navigation in screen and no there is no scrolling. | The user can Download yallakora app from app store or google play and the app should be accessable. | no test data nedded | 1-open yallakora app. 2-navigate to 'بطولات'. 3- click on 'دوري وي المصري'. | no preview for full name of teams table rank and league ui issue and there is no navigation in screen | ui fit with screen, scrolling option, full name preview | Moderate | Low | https://drive.google.com/file/d/15oI88JxDsgYFLlJAE3lYXpZy1L-eNTPr/view?usp=sharing | Samsung Galaxy A6+ One Ui version 2.0 Android Version 10 | Wifi/Data | Developer X | To Do
YallaKora_010 | Favoirite Teams 'فرقك' | edit button should be hidden if there is no favorite teams | The user can Download yallakora app from app store or google play and the app should be accessable. | no test data nedded | 1-open yallakora app. 2-navigate to 'فرقك'. | edit button not hidden if favorite list is empty. | edit button should be hidden if there is no favorite teams | Major | Medium | https://drive.google.com/file/d/1H2Zu1hVRKjeasrYT-eA4Kr0SRqdqzqqL/view?usp=sharing | Samsung Galaxy A6+ One Ui version 2.0 Android Version 10 | Wifi/Data | Developer X | To Do
YallaKora_011 | Favoirite Teams 'فرقك' | no back button in selection of favorite teams | The user can Download yallakora app from app store or google play and the app should be accessable. | no test data nedded | 1-open yallakora app. 2-navigate to 'فرقك'. | no back button | should be back option | Major | Hight | https://drive.google.com/file/d/1hBIidZcJA-a5tDLzalj5SOY6eQES6Lo9/view?usp=sharing | Samsung Galaxy A6+ One Ui version 2.0 Android Version 10 | Wifi/Data | Developer X | To Do
YallaKora_012 | Leagues'بطولات' | no statistics for emirates league 'الدوري الاماراتي' | The user can Download yallakora app from app store or google play and the app should be accessable. | no test data nedded | 1-open yallakora app. 2-navigate to 'بطولات'. 3- click on 'دوري الامارات'. 4- navigate to statistics | no content | content should be preview | Major | Medium | https://drive.google.com/file/d/1Z84PNRLawA0zWDk4Hz6gZFHkL160c1if/view?usp=sharing | Samsung Galaxy A6+ One Ui version 2.0 Android Version 10 | Wifi/Data | Developer X | To Do
YallaKora_013 | Home 'الرئيسية' | proximity of design and tab pressed behavior not suitable for user | The user can Download yallakora app from app store or google play and the app should be accessable. | no test data nedded | 1-open yallakora app. | proximity of design and tab pressed behavior not suitable for user | tab pressed behavior and proximity should be optmize | Minor | Low | https://drive.google.com/file/d/1x6qO9ilyjCQVGnZ817R6AgDuZTNXRnWF/view?usp=sharing | Samsung Galaxy A6+ One Ui version 2.0 Android Version 10 | Wifi/Data | Developer X | To Do
YallaKora_014
YallaKora_015
YallaKora_016